## Segment 1
| Main Tasks | Requirements | Programs Used/Outcome | Assigned To | Progress/Task Completion | Tasks for Next Meeting | Additional Notes-All Times in Pacific | Grading
Segment 1 Sketch It Out Decide on your overall project, select your question, and build a simple model. Then prototype your idea by using either CSV or JSON files to connect the model to a fabricated database. Due: Wed 01/25 | GitHub repository | - Branches - README file - Commits - Update project's progress, links and important references, slide deck… |  | Alice, Zeinab, Michael Yash: GitHub merging branches | In progress | - Choose a title and update github - Merge github branches and create clean process for clean files | - Alice, Michael, Zeinab(zoom) Friday @2:30, make sure to work on the storyboard Yash joining @3 to go over Github merging branches | Content (60 points) - A detailed README.md file (20 points) - At least four commits per team member (20 points) - A database that stores at least two tables (or collections) for the project (20 points) Presentation (40 points) - The selected topic and the reasoning for that selection (20 points) - A description of the data (20 points) - The questions that the team plans to answer with the project (20 points)
| Reasoning behind the selected topic & its factors | - Suicide rates - Factors: Gender, Age, Countries, Alcohol, Education, Employment, Healthy Spending, Obesity, Poverty Rate, Smoking |  | Team | In progress | - Write up readme for the topic selection process and for the data explatory process
| Questions our data will answer | - Is there a correlation between suicide risk and socio-economic status and/or health data? -What significant impact suicide risk the most? |  | Alice - clean Alcohol data, clean Social Support Michael - clean Smoker, clean Social Spending Maria - clean Employment, Obesity Alvin - clean Poverty Zeinab - clean Education Yash - clean Health Spending, Suicide Rate | In progress
| ETL-Data |  | - Python/Pandas library - Jupyter - CSV file | Team | In progress | - Combine datasets | - Maria will finish by tomorrow
| Database-ERD Mock-up | - Description of how ERD integrates into the database and works with the code - Database need to contain at least two tables or collections | - Postgres??? | Alice | In progress | - Database creation - Merge Tables - Export into CSV - Imported into Python | - Maria, Zeinab(zoom) Sat @2:30
| Machine Learning Model Mock-up | - Why did you choose this model? - How will you train the model? - What’s the accuracy of the model? - How does the model work? - If statistics are involved, which ones will the analysis include, and why? - What would you include or change if you had more time? | - Supervised machine learning, linear regression, oversampling, random forest. | Michael, Yash, Alvin | In progress |  | Michael, Yash, Alvin(zoom) - Friday @4 - Sunday @11
| Dashboard/Storyboard | - At least one interactive element to be demonstrated in real time during the presentation | - Tableau | Alice, Zeinab, Alvin | In progress
| Communication Strategy |  | - Slack, Zoom - Meeting 3x/week excluding classes | Team | Completed |  | - Team Sat @3:30 - Team Sun @1:00 Zeinab(zoom)

## Segment 2
| Main Tasks | Requirements | Programs Used/Outcome | Assigned To | Progress/Task Completion | Tasks for Next Meeting | Additional Notes | Grading
Segment 2 Build and Assemble Train your model, build the database that you'll use for your final presentation, and create both your dashboard and your presentation. Due: Wed 02/01 | GitHub | - Create a new GitHub branch to work from during this segment -Diving into GitHub peer review tools, You'll merge pull requests (PRs) in your separate branches and create new ones for the tasks in this segment - The branches that were originally created for each person should be merged into the main branch and new branches should be created for each task - README file: Description of the Machine Learning Model. and discussion of any preprocessing that's involved, an interpretation of the accuracy, precision, and sensitivity of the model should be included with the submission. | -Machine Learning description to add to README 35% accuracy using the dataset with the average values Michael and Alvin Readme update-Alice |  |  |  | Add to README: https://hackernoon.com/my-notes-on-mae-vs-mse-error-metrics -Add MAE and MSE -Update question: Identifying factors that impact suicide OR -Which factors have a correlation to suicide rates | Content (80 points) - A detailed README.md file that includes the project status, images, descriptions, and results (20 points) - At least eight total commits per team member (20 points) - A machine learning model, including a confusion matrix and accuracy score (20 points) - Database that stores data for the project with at least two tables or collections (20 points) Presentation (20 points) - The selected topic and the reasoning for that selection (2 points) A description of the data (3 points) - The questions that the team originally planned to answer with the project (2 points) - A description of the data exploration phase of the project (5 points) - A description of the analysis phase of the project (5 points) - The technologies, languages, tools, and algorithms that the team used throughout the project (3 points)
| Technical | - Keep track of any changes in the database, and update the ERD whenever the schema changes, - Complete a final round of code testing to make sure everything runs without errors - Test the database integration and Machine Learning Model - Find weaknesses and loopholes | Alice-ERD |  |  |  | Assignments: - Presentation Alice, Yash, Zeinab - Github updates Team - ReadMe Yash - Interactive Dashboard Alice, Yash, Zeinab - Weakness and Loophole Documentation for Model Maria - Machine Learning Model Team
| Refining the Analysis | - Include generating at least three images to use both in the presentation and with the dashboard, images need to be neat, clean and add weight to the data story- incorporate a visualization library for high quality images(Ex: Python/Seaborn)
| Final Dashboard | - Creating an outline before starting the final product to smooth out the creation process - Main visualizations, interactive element, | -Create an outline for the dashboard in Tableau and integrate visualization and at least one interactive element.Yash
| Pre-presentation | To wrap up, team members should do the following: - Peer review each others’ code - Draft the presentation in Google Slides - If needed, continue to refine the code (including the machine learning and database integration) and the images that the presentation will include - What we would have done differently if we had more time
| Presentation | - Use as little text as possible, and focus on communicating only the most essential information, make the presentation enjoyable
Communication/Additional

## Segment 3
| Main Tasks | Requirements | Programs Used/Outcome | Assigned To | Progress/Task Completion | Tasks for Next Meeting | Additional Notes | Grading
Segment 3 Put It All Together Put the final touches on your model, database, and dashboard. Then create and deliver your final presentation to the class. Submit the written assessment. Due: Wed 02/08 | Final Presentation | Presentation must include: 1- Reasoning behind the selected topic and the questions we planned to answer. 2- Description of the data source, data exploration phase, and data analysis phase. 3- Technologies, languages, tools and algorithms used. 4- Result of the analysis and recommendations for the future. 5- What we would have done differently if we had more time. 6- Presenting in equal proportions per team member limited to the time provided by the instructor. | [5 empty] | Content (30 points) - A detailed README.md file that includes the project status, images, descriptions, and results. (5 points) - At least 12 total commits per team member. (5 points) - A machine learning model, including a confusion matrix and an accuracy score. (10 points) - A database that stores the data for the project and that contains at least two tables or collections (5 points) - A dashboard that has at least one interactive element. (5 points) Presentation (70 points) - The selected topic and the reasoning for that selection. (6 points) - A description of the data source. (6 points) - The questions that the team planned to answer with the data. (6 points) - A description of the data exploration phase of the project. (6 points) - A description of the analysis phase of the project. (6 points) - The technologies, languages, tools, and algorithms that the team used throughout the project. (10 points) - The results of the analysis. (10 points) - Any recommendations for a future analysis. (10 points) - Anything that the team would have done differently if they had more time. (10 points) All the team members present in equal proportions. The team demonstrates the interactivity of the dashboard in real time. The presentation falls within any time limits that the instructor provides.
| Written Assessment | 1- Self-assessment must include: - Cohesive written analysis: Role or roles played and its contribution to the project. Greatest personal challenge over the course of the project and how you overcame it. 2- Project and team summary must include: - Two paragraph written analysis summarizing the project, illustrating the teamwork of the group and documenting the lessons learned. - The summary should be written as if to be used in an interview or cover letter which includes communication protocols, challenges and overcoming them, what would you do differently next time. In addition, team strengths(tips and tricks), topic addressed, machine learning model used and results of the analysis.